## 项目日程安排
在此工作表中创建项目日程安排。 在单元格 B1 中输入此项目的标题。 有关如何使用此工作表（包括屏幕阅读器的说明）以及此工作簿作者的信息包含在“关于”工作表中。 继续向下浏览 A 列，获取进一步指示。 | Timeline-赛诺菲卒中视频6条
在单元格 B3 中输入项目主管的姓名。在单元格 E3 中输入项目开始日期。项目开始：标签位于单元格 C3 中。 |  | 2020-09-28
单元格 E4 中的显示周数表示单元格 I4 中项目日程安排内显示的起始周数。项目开始日期视为第 1 周。要更改显示周数，只需单元格 E4 中输入新的周数。 从单元格 E4 的显示周数开始，每周的开始日期从单元格 I4 开始并且说自动计算得出的。在该视图中，从单元格 I4 到单元格 BF4 共有 8 周的时间。 请勿修改这些单元格。 显示周数：标签位于单元格 C4 中。 |  | 1 |  |  | 2020年9月 |  |  |  | 2020年10月 | [30 empty] | 2020年11月
单元格 I5 到 BL5 包含每个日期单元格上方单元格块中表示的星期的日期数字并且是自动计算得出的。 请勿修改这些单元格。 今天的日期带有红色（十六进制 #AD3815）轮廓（从第 5 行中显示今天日期的列及至项目日程安排结尾的该列）。 | time axis 2020-09-27 to 2020-11-30
此行包含其后面的项目日程安排的标题。 从 B6 浏览到 BL6 以获取内容。该标题上方日期一周中每一天的首字母，从单元格 I6 开始，直到单元格 BL6。 所有项目日程表图表都是根据输入的开始和结束日期使用条件格式自动生成的。 从单元格 I7 开始的列 I 之后，请勿修改列内单元格中的内容。 | 任务 | 开始日期 | 结束日期 | 天数 | time axis 2020-09-27 to 2020-11-30
请勿删除此行。隐藏了此行，以保留用于突出显示项目日程安排中当天的公式。
单元格 B9 包含示例任务“任务 1”。 在单元格 B9 中输入新的任务名称。 在单元格 C9 中输入任务负责人。 在单元格 D9 中输入任务进度。进度条出现在单元格中，并根据单元格中的数字进行着色。例如，50% 的进度将着色一半的单元格。 在单元格 E9 中输入任务开始日期。 在单元格 F9 中输入任务结束日期。 从单元格 I9 到 BL9 的块中显示输入日期的已着色状态栏。 | 提供分镜脚本 客户提出修改意见 | 2020-09-28 | 2020-09-29 | 2
第 10 行到第 13 行重复第 9 行的模式。 请对此工作表中的所有任务行重复单元格 A9 中的指令。覆盖任何示例数据。 另一个阶段的示例从单元格 A14 开始。 继续在单元格 A10 到 A13 中输入任务或转到单元格 A14 了解详细信息。 | 分镜脚本定稿 | 2020-09-30 | 2020-09-30 | 1
| 拍摄前准备 道具 服装等 | 2020-10-01 | 2020-10-08 | 8
| 确认演员人选、协调拍摄场地等内容 | 2020-10-09 | 2020-10-16 | 8
| 选择2天完成拍摄 | 2020-10-17 | 2020-10-22 | 6
| 提交初稿 客户提出修改意见 | 2020-10-27 | 2020-11-01 | 6
| 提交二稿 调色 精剪 配乐 客户提出修改意见 | 2020-11-06 | 2020-11-06 | 1
| 提交三稿 客户提出修改意见 | 2020-11-11 | 2020-11-16 | 6
| 定稿 | 2020-11-18 | 2020-11-18 | 1

## 所有文献资料详情 (hidden)
文件 | 一级子文件 | 二级子文件 | 三级子文件 | 文件类型 | 页数
文件夹一：品牌资料 BRANDING MATERIALS | 7个子文件夹 | 1. (旧档案，仅供参考)小册子 (Old file, just for reference) Brochure：Dose Matters Renal Sales Aid+E-Detailer | Nephro_AdultBody_diagram_signs&symptoms Helvetica reference | pdf | 1
|  |  | FZ-Renal-Sales-Aid | pdf | 12
|  | 2. (旧档案，仅供参考)小册子 (Old file, just for reference) Brochure：The Benefits of Early Treatment with Fabrazyme 1mgkg2 Weeks HCP Brochure | Early Treatment with Fabrazyme Brochure 16 pages Updated 8-15-17 v2 | pdf | 9
|  | 3. 动画：Fabrazyme动作动画机制 Animation：Fabrazyme Mechanism of Action Animation | Fabrazyme-MOA-5-22-17 | word | 3
|  | 4. 动画：Fabry肾脏内科动画 Animation：Fabry Nephro Animation | Nephro_22.01 | ppt | 66
|  |  | Video Script in PDF with Reference | pdf | 3
|  | 5. Fabrazyme15年 Fabrazyme 15 year - Booklet Past | GEN0442 OS 15 jaar fabry WTHR A5 form | pdf | 2
|  |  | GEN0442 BW 15 jaar fabry WTHR2 A5 form | pdf | 72
|  |  | FINAL HISTORY BOOKLET | pdf | 41
|  | 6. Fabrazyme分子 Fabrazyme_Molecule | 无 |  | 0
|  | 7. logo | 无 |  | 0
| 16个pdf | pdf1 | (旧文件，仅供参考)德国10年成果出版物2015再版 (Old file, just for reference) Germain-10year-Outcome-Publication-2015-Reprint-Carrier | pdf | 2
|  | pdf2 | （旧文件，仅供参考）观察不同剂量的疗效 (Old file, just for reference) INSIGHTS IN EFFICACY OF DIFFERENT DOSAGE | pdf | 3
|  | pdf3 | 38.5 x 45.5_Severe Clinical Events 2019 4 Doctors v1 | pdf | 4
|  | pdf4 | 2019 Disrupt the Threat Rebrand 4 Doctors 8-1-19 | pdf | 4
|  | pdf5 | 2019 FZ Early Treatment SAGLB.FABR.17.01.0067(1)b Revised | pdf | 20
|  | pdf6 | 2019_10YrOutcome_45x36_horizontal_Rebranded 4 Doctors v2 | pdf | 8
|  | pdf7 | Fabrazyme_BrandBook-8-22-19 hi-res | pdf | 30
|  | pdf8 | 使用指南 Fabrazyme-Infusion-Guidance | pdf | 5
|  | pdf9 | Fabry_10 Year Germain Reprint All 4 Doctors v2 | pdf | 8
|  | pdf10 | fabry-family-tree-insert | pdf | 2
|  | pdf11 | fabry-family-tree-pocketfolder | pdf | 2
|  | pdf12 | Fabry-Find-the-Roots-ICIEM-SAGLB.FABR.17.01.0046a | pdf | 20
|  | pdf13 | FZ Kramer Reprint Carriers combined doctors SAGLB.FABR.18.01.0018a v1 | pdf | 8
|  | pdf14 | FZ LCD Screen Rebranded 2019 All 4 Doctors v2 | pdf | 8
|  | pdf15 | FZ Renal Sales Aid 2019 New Branding FINAL | pdf | 15
|  | pdf16 | FZ_CVA_8-28-19 lo res | pdf | 32
文件夹二：Fabrazyme和Replagal比较 Fabrazyme vs Replagal | 3个子文件夹 | 1. 研究 INFORM Study Switching Study | 978-3-662-49668-8_Chapter_483 | pdf | 12
|  |  | pub-inform-2015-presentation | pdf | 31
|  | 2. 回顾性队列研究 Retrospective Cohort Study | jmedgenet-2017-104863.full | pdf | 8
|  | 3. 系统评价 Systematic Review | El Dib R et al. PLoS One. 2017 Mar 15 | pdf | 22
文件夹三：法布雷出版物 Fabry Publication | 5个子文件夹 | 1. FABRAZYME临床研究 FABRAZYME CLINICAL STUDIES | [2001] FD中酶替代治疗的1、2期临床试验 A Phase 1，2 Clinical Trial of Enzyme Replacement in FD | pdf | 12
|  |  | [2001] 法布里病：临床前研究证明了α-半乳糖苷酶A替代在缺乏酶的小鼠中的有效性 Fabry Disease：Preclinical Studies Demonstrate the Effectiveness of α-Galactosidase A Replacement in Enzyme-Deficient Mice | pdf | 12
|  |  | [2001] 重组人α-半乳糖苷酶替代疗法在FD中的安全性和有效性 Safety and Efficacy of Recombinant Human α-Galactosidase a Replacement Therapy in FD | pdf | 8
|  |  | [2002] ERT后，多种细胞类型清除了法布里肾脏中的GL-3积累 GL-3 accumulation in the Fabry kidney is cleared from multiple cell types after ERT | pdf | 14
|  |  | [2004] 通过重复皮肤活检监测FD对ERT的3年疗效 Monitoring the 3-Year Efficacy of ERT in FD by Repeated Skin Biopsies | pdf | 9
|  |  | [2007] 阿加糖酶-β疗法治疗晚期FD：随机对照试验 Agalsidase-Beta Therapy for Advanced FD： ARandomized Trial | pdf | 12
|  |  | [2007] FD患者经Agalsidaseβ治疗54个月后持续，长期肾脏稳定 Sustained, Long-Term Renal Stabilization after 54 months of Agalsidase β Terapy in Pts with FD | pdf | 11
|  |  | [2009] 针对半乳糖苷酶的IgG抗体对ERT期间FD疗效的潜在影响的回顾性分析 A retrospective analysis of the potential impact of IgG antibodies to agalsidase β on efficacy during ERT for FD | pdf | 9
|  |  | [2009] ERT前后心内膜活检FD评估中的心脏微血管病理学 Cardiac Microvascular Pathology in FD Evaluation of Endomyocardial Biopsies before and after ERT | pdf | 9
|  |  | [2009] 在接受FD的ERT患者中，在标准治疗剂量后评估低剂量的半乳糖苷酶β Evaluation of a low dose, after a standard therapeutic dose, of agalsidase β during ERT in pts with FD | pdf | 7
|  |  | [2015] 从阿加糖酶阿尔法转换为阿加糖酶β作为FD的ERT后血浆GL-3水平降低 Reduction of Plasma GL-3 Levels after Switching from Agalsidase Alfa to Agalsidase Beta as ERT for FD | pdf | 12
|  | 2. FABRAZYME注册登记出版物 FABRAZYME REGISTRY PUBLICATIONS | [2010] 阿加糖苷酶β治疗与FD患者的生活质量改善相关：法布里注册中心的发现 Agalsidase β treatment is associated with improved quality of life in pts with FD：Findings from the Fabry Registry | pdf | 10
|  |  | [2012] 抗α-半乳糖苷酶A抗体对半乳糖苷酶β治疗的反应：法布里注册表提供的数据 Anti-α-galactosidase A antibody response to agalsidase β treatment：Data from the Fabry Registry | pdf | 7
|  |  | [2012] 阿加糖酶β治疗肾功能衰竭的肾结局：蛋白尿作用和治疗开始时间 Renal outcomes of agalsidase β treatment for FD：role of proteinuria and timing of treatment initiation | pdf | 8
|  |  | [2013] 未经治疗的男性和经半乳糖苷酶β治疗的男性左心室质量的分析：来自Fabry Registry的数据 Analysis of left ventricular mass in untreated men and in men treated with agalsidase β：data from the Fabry Registry | pdf | 8
|  |  | [2015] FD患者中用阿糖苷酶β治疗ERT的十年结局 Ten-year outcome of ERT with agalsidase β in pts with FD | pdf | 6
|  | 3. 指南和共识 Guideline & Consensus | [2006] 法布里病：多器官系统参与的评估和管理指南 Fabry Disease：Guidelines for the evaluation and management of multi-organ system involvement | pdf | 10
|  |  | [2008] 成人法布里肾病的诊断和治疗建议和指南 Recommendations and guidelines for the diagnosis and treatment of Fabry nephropathy in adults | pdf | 10
|  |  | [2010] 法布里病患者的心脏挑战 Cardiac challenges in patients with Fabry disease | pdf | 8
|  |  | [2010] 酶替代疗法和法布里肾病 Enzyme Replacement Therapy and Fabry Nephropathy | pdf | 8
|  |  | [2010] 法布里病诊断指南 Fabry disease diagnostic guideline | pdf | 8
|  |  | [2013] 中国法布里病(Fabry病)诊治专家共识 | 中文 | 0
|  |  | [2016] FD儿童的管理和治疗：基于美国的观点 The Management and treatment of children with FD：A United States-based perspective | pdf | 10
|  |  | [2018] 欧洲专家就法布里病治疗目标达成共识 European expert consensus statement on therapeutic goals in Fabry disease | pdf | 15
|  |  | [2018] 再谈法布里病：成年患者的治疗建议 Fabry disease revisited：Management and treatment recommendation for adult pts | pdf | 12
|  | 4. 法布雷病的自然史 NATURAL HISTORY OF FABRY DISEASE | [2004] 导致FD的分子缺陷：人α-半乳糖苷酶的结构 The Molecular Defect Leading to FD：Structure of Human α-Galactosidase | pdf | 17
|  |  | [2008] Fabry Registry中352例小儿患者的FD表征 Characterization of FD in 352 Pediatric Patients in the Fabry Registry | pdf | 6
|  |  | [2008] 通过家族病史诊断FD Diagnosis of FD via Analysis of Family History | pdf | 5
|  |  | [2008] 法布雷病 Fabry's disease | pdf | 9
|  |  | [2008] FD的女性经常累及主要器官：法布里注册中心的经验教训 Females with FD frequently have major organ involvement：Lessons from the Fabry Registry | pdf | 17
|  |  | [2008] FD男女肾病：ERT治疗前患者的横断面描述 Nephropathy in males and females with FD：cross-sectional description of patients before treatment with ERT | pdf | 8
|  |  | [2008] FD的眼部特征：诊断危及生命的疾病 Ocular Features of FD：Diagnosis of a Treatment Life-threatening Disorder | pdf | 8
|  |  | [2008] FD和最小蛋白尿的儿童和青少年的肾脏活检结果 Renal Biopsy Findings in Children and Adolescents with FD and Minimal Albuminuria | pdf | 10
|  |  | [2009] 法布里病：肾病的进展以及ERT前心脑血管事件的发生率 Fabry Disease：progression of nephropathy, and prevalence of cardiac and cerebrovascular events before ERT | pdf | 10
|  |  | [2009] FD男性和女性的预期寿命和死亡原因 Life expectancy and cause of death in males and females with FD | pdf | 7
|  |  | [2009] 诊断前和没有其他临床事件时常发生FD中风 Stroke in FD Frequently Occurs before Diagnosis and in the Absence of Other Clinical Events | pdf | 7
|  |  | [2010] FD患者的终末期肾脏疾病：来自法布里注册表的自然历史数据 End-stage renal disease in patients with FD：natural history data from the Fabry Registry | pdf | 7
|  |  | [2010] 法布雷病 Fabry Disease | pdf | 49
|  |  | [2010] FD成人肾病进展的预后指标：法布里登记处的自然历史数据 Prognostic Indicators of Renal Disease Progression in Adults with FD：Natural History Data from the Fabry Registry | pdf | 15
|  |  | [2011] FD患者的心血管事件 Cardiovascular Events in Patients with FD | pdf | 7
|  |  | [2011] 外周神经系统参与FD的早期诊断和神经性疼痛的治疗 Early diagnosis of peripheral nervous system involvement in FD and treatment of neuropathic pain | pdf | 11
|  |  | [2011] 青年FD患者进行性足细胞损伤和GL-3积累 Progressive Podocyte Injury and GL-3 Accumulation are Progressive in Young Patients with FD | pdf | 9
|  |  | [2013] FD左室肥厚：一种实用的诊断方法 Left ventricular hypertrophy in FD：a practical approach to diagnosis | pdf | 8
|  |  | [2014] FD筛查的系统评价：具有未知意义遗传变异的个体的患病率 A systematic review on screening for FD：prevalence of individuals with genetic variants of unknown significance | pdf | 25
|  |  | [2015] FD的当前状态中的心血管介入 Cererovascular Involvement in FD Current Status of Knowledge | pdf | 12
|  |  | [2015] 初治男性小儿FD的早期疾病状态的表征 Characterization of Early Disease Status in Treatment-Naive Male Paediatric Pts with FD | pdf | 19
|  |  | [2015] 婴幼儿法布里疾病：系统的文献综述 Fabry disease in infancy and early childhood：a systematic literature reivew | pdf | 8
|  |  | [2015] 足突磨蚀是年轻经典法布里患有白蛋白尿患者的肾病早期标志物 Foot Process Effacement is an Early Marker of Nephropathy in Young Classic Fabry Patients withour Albuminuria | pdf | 6
|  |  | [2016] 女性FD患者的X染色体失活 X-chromosome inactivation in female patients with FD | pdf | 11
|  | 5. 其他相关出版物 OTHER FABRAZYME PUBLICATIONS | [2003] ERT对糖脂贮积病FD的生化和药理比较 A biochemical and pharmacological comparison of ERT for the glycolipid storage disorder FD | pdf | 9
|  |  | [2006] 比较半乳糖苷酶α和半乳糖苷酶β对培养的人法布里成纤维细胞和法布里小鼠的作用 Comparison of the effects of agalsidase α and agalisidase β on cultured human Fabry fibroblasts and Fabry mice | pdf | 9
|  |  | [2007] FD的治疗：以0.2 mg / kg的剂量使用阿糖苷酶α或β进行比较试验的结果 Treatment of FD：Outcome of a comparative Trial with Agalsidase α or β at a dose of 0.2 mg per kg | pdf | 10
|  |  | [2008] 糖苷酶不同剂量方案治疗FD：对抗体形成和GL-3的影响 Treatment of FD with different dosing regimens of agalsidase：Effects on antibody formation and GL-3 | pdf | 7
|  |  | [2009] FD的酶替代疗法 Enzyme Replacement Therapy for FD | pdf | 27
|  |  | [2013] 阿加糖苷酶使年轻患者的FD受益于肾脏组织学检查 Agalsidase Benefits Renal Histology in Young Pts with FD | pdf | 12
|  |  | [2013] 儿童法布里病：阿糖苷酶-β酶替代治疗 Fabry Disease in Children：agalsidase-β enzyme replacement therapy | pdf | 7
|  |  | [2014] FD的ERT稳定白质病变进展 ERT Stabilized White Matter Lesion Progression in FD | pdf | 9
|  |  | [2014] 法布里病：剂量问题 Fabry Disease：Dose Matters | pdf | 3
|  |  | [2014] 减少ERT后的FD患者与治疗切换 Patients with FD after ERT reduction versus treatment switch | pdf | 13
| 9个pdf | pdf1 | [2009] 台湾人群中NBS揭示的FB心脏变异的高发生率 High incidence of the cardiac Variant of FB revealed by NBS in the Taiwan Chinese population | pdf | 8
|  | pdf2 | [2011] ERT后经典法布里病患者血浆Lyso-Gb 3升高的减少 Reduction of elevated plasma globotriaosylsphingosine in patients with classic Fabry disease following ERT | pdf | 7
|  | pdf3 | [2014] 法布里肾病：综述-如何优化法布里肾病的治疗 Fabry nephropathy：a review-how can we optimize the management of Fabry nephropathy | pdf | 13
|  | pdf4 | [2016] 成年FD接受阿糖苷酶β治疗的FD患者的治疗时间获益：FD的数据 Time to treatment benefit for adult patients with FD receiving agalsidase β：data from the FD | pdf | 8
|  | pdf5 | [2017] 典型和非典型法布里病的特征 Characterization of Classical and Nonclassical Fabry Disease | pdf | 11
|  | pdf6 | [2017] 酶替代疗法下的法布里病 Fabry disease under enzyme replacement therapy【治疗剂量疗效】 | pdf | 11
|  | pdf7 | [2017] 长期剂量依赖性阿糖苷酶对法布里肾脏组织的影响 Long Term Dose Dependent Agalsidase Effects on kidney histology in Fabry【治疗剂量疗效】 | pdf | 10
|  | pdf8 | [2018] 法布里病：新生儿筛查的回顾与经验 Fabry Disease：Review and experience during newborn screening | pdf | 8
|  | pdf9 | [2018] 法布里肾病：循证叙事回顾 Fabry Nephropathy：An Evidence - Based Narrative Review | pdf | 16
文件夹四：幻灯片 Slides Decks | 2个子文件夹 | 1. 圆桌会议 Round Table Discussion | 2018年3月15日，哥伦比亚 2018 Ortiz colombia march 15 elderly | ppt | 14
|  |  | 2018年，卡塔赫纳 Trimarchi CARTAGENA-2018 | ppt | 24
|  |  | 2018年，拉丁美洲 Jaurretche_ERT.start.RT.LATAM.2018 | ppt | 16
|  |  | 哥伦比亚 Dr Perreta - Mujeres Colombia | ppt | 24
|  |  | 2018，拉丁美洲，儿童治疗 Dr Fainboim Children treatment.RT.LATAM.2018 | ppt | 16
|  |  | 拉丁美洲 Cabrera_Charla Enfermedad de Fabry. LATAM 2018 | pdf | 93
|  |  | 肾活检 Marlene Antonia - Renal Biopsies | pdf | 121
|  |  | 卡塔赫纳 meeting CARTAGENA POLITEI | 文件损坏 | 0
|  |  | 2018年4月5日，哥伦比亚大学 MJ HILZ Fabry lessons learned about diagnosis treatment Columbia 5th April 2018 | 文件损坏 | 0
|  | 2. 培训 Training | 1.关于诊断和治疗 Lessons Learned about Diagnostics and Treatment_Ortiz | ppt | 56
|  |  | 2. 症状和体征 Signs and symptoms of FD_Sergio Salgado | ppt | 37
|  |  | 3.当前诊断方法 Current approaches to laboratory diagnostics of FD _Zakharova | ppt | 35
|  |  | 4. 肾活检的重要性 Importance of Renal Biopsies_Ortiz | ppt | 48
|  |  | 5. 家族关系 Family Tree the liaison bewteen relatives_Juan Politei | ppt | 24
|  |  | 6. 法布雷病的肾脏反应 Nephrological manifestations of FD_Trimarchi | ppt | 54
|  |  | 7. 法布雷病的心脏学表现 Cardiological manifestations of FD_Gustavo Cabrera | ppt | 38
|  |  | 8.法布雷病的神经学表现 Neurological manifestations of FD_Max Hilz | ppt | 92
|  |  | 9. 法布雷病患者诊断和治疗反应的有效标志物 Useful marker of diagnosis and treatment response in patients with FD_Juan Politei | ppt | 22
|  |  | 10.用于儿童、妇女和老人的治疗 Dillemas in FD When to treat children, women and elderly_Fernando Perreta 其他 | ppt | 48
|  |  | 11. 在ERT现有治疗方法，真正重要的是什么？ Fabry Disease - Current Approaches in ERT. What really matters_Max Hilz | ppt | 111
| 1个幻灯 | ppt1 | 法布雷病标准幻灯片集 Fabry Disease Standard Slide Set | pdf | 80
文件夹五：视觉引导患者 Visual Guide Patient | 3个子文件夹 | 1. 高分辨率 High Resolution | 共60个 | pdf | 60
|  | 2. 低分辨率 Low Resolution | GVPE0022_defiris | pdf | 68
|  | 3. 生产文件 Production File | 无
总和 |  |  |  |  | 2258